## Sheet1
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8
| 9/28/2023 - 10/5/2023 | 10/5/2023 - 10/12/2023 | 10/12/2023 - 10/19/2023 | 10/19/2023 - 10/26/2023 | 10/26/2023-11/2/2023 | 11/2/2023-11/9/2023 | 11/9/2023-11/16/2023 | 11/16/2023-11/23/2023
Shiva
What tasks did I work on / complete? | understanding the project's requirements creating the UI wireframes for arrival and departure schedules functionality | Devloped UI wireframes for Login page and Home Page, developed UI design for gate assignment | developed the UI for adding movies,integrated movie schedule page on frontend and backend | developing the theatre employee screen for the website, frontend/backend | displayinganalytics page,Added theatre employee UI modifications | developing the updated schedule for airline employee frontend | added validations for update schedule | website bug fixes and updated user interface
What am I planning to work on next? | create the basic framework,mock login page | developing functionalities for theatre Employee,sign in page mock. | developed Enable or disable one or more gates for maintenance | adding validations and displaying data based on selection of inputs for theatre employee | displaying last 30 days watched summary frontend | developing the updated schedule for airline employee backend,Merge backend and frontend for theatre employee | bug fixes and minor UI changes | updated UI for update schedule
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #7
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: we discussed our task progress in the daily meeting and solved any blockers we faced together (XP value: feedback and Simplicity)
Mahek
What tasks did I work on / complete? | Determining entities,attributes along with the relationship | Understanding flow of adding and updating schedule for theatre employee DB Design and table creation, mock data for all tables and UI wireframe for login and various roles details page | Developed UI for Home Page frontend and backend | Developed showtime schedule page and profile page frontend | updated rewardsl information for movie booking | Developed UI and backend implementation for admin authority page | Developed add theatre for theatre employee frontend | Developed backend implementation for the system to prevent conflicting assignments,minor bug fixes and testing the complete flow of the application
What am I planning to work on next? | Table creation and DB design,mock data for all tables | creating wireframe for add schedule page,Created customer entities and relationships | Developed UI for Login and Signup Page for frontend,integrated movie schedule page on frontend and backend | Integrated login and signup page on frontend,added rewards points | displaying last 30 days watched movies frontend | Implementing Required Validations on theatre employee,Merge backend and frontend for theatre employee | Developed add theatre for theatre employee backend,updated UI for update schedule | Fix issues in movie schedule page & login page
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #8
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Through regular meetings, everyone discussed functionalities in details which help us achieved the well reviewed solution.; Week #7: Communication with the team related to integration and testing
Charan
What tasks did I work on / complete? | Architecture diagram ,UI wireframe for login page and Home page | Design and creation of tables namely movies, theatre, schedules DB and review with the team. | Designed and implemented signin and navigation for home page on frontend | Integrated profile page and analytics on frontend. | updated analytics page. | Developed random assignment of gate for arrival and departing flights | Developed add movie for theatre employee frontend | Developed backend implementation for the system to prevent conflicting assignments,minor bug fixes and testing the complete flow of the application
What am I planning to work on next? | DB design | Created UI wireframe for login and theatre employee,Design Seat booking UI | Integrated signup and login on backend. | updated analytics based on 2filters, updated showtime information | Added Theatre and Movie details | Developed UI and backend implementation for admin authority page | Developed updated add movie for theatre employee frontend and backend | Minor bug fixes, hosting the application on aws
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #8
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Communication - Discussion about technology stack and requirements | Communication - Discussed about the design decisions with the team and got it reviewed. | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication with the team related to approach. | Communication with the team related to approach and integrations