## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sprint
| Table 1 | Sprint
Burndown
| Table 1 | Burndown

## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 10 hrs x 2 weeks x 4 people) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24
|  |  |  | 80 | 72 | 66 | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0 | Ideal Burndown
|  |  | 80 | 80 | 79 | 71 | 68 | 59 | 52 | 49 | 46 | 0 | 0 | 0 |  |  |  | Remaining Hrs (Total)
HLD and Document Requirement | Document abstract with all requirements | Siva Swaroop vardhineedi | 10 | 2023-09-11: 10; 2023-09-12: 9; 2023-09-13: 8; 2023-09-14: 7; 2023-09-15: 5; 2023-09-16: 2; 2023-09-17: 1; 2023-09-18: 0
| UML diagram | Mahek Virani | 30 | 2023-09-11: 30; 2023-09-12: 30; 2023-09-13: 25; 2023-09-14: 25; 2023-09-15: 20; 2023-09-16: 18; 2023-09-17: 18; 2023-09-18: 16
| Tech Stack finalizing based on design | Sri Charan Reddy Mallu | 40 | 2023-09-11: 40; 2023-09-12: 40; 2023-09-13: 38; 2023-09-14: 36; 2023-09-15: 34; 2023-09-16: 32; 2023-09-17: 30; 2023-09-18: 30
| IDE and Github setup | Ruthwik | 10 | 2023-09-11: 10; 2023-09-12: 10; 2023-09-13: 10; 2023-09-14: 10; 2023-09-15: 10; 2023-09-16: 10; 2023-09-17: 10; 2023-09-18: 10
Team:
Siva Swaroop vardhineedi | 10 hours / Week
Mahek Virani | 10 hours / Week
Sri Charan Reddy Mallu | 10 hours / Week
Ruthwik | 10 hours / Week
Total Available Hours During Sprint: | 80